| 活动 Activities | 活动描述 Description |
| --- | --- |
| 增扩PDT，进行产品开发全员任命 Identify Extended Team Members IPMT-50 | 确定项目开发、验证和发布阶段后续工作的外围组成员并按合同分配资源。 Identify extended team members for continuing work on the project through the develop, qualify and launch phases, and allocate resources per the contract |
| 更新项目环境 Update Project Environment POP-30 | 更新项目文档及数据库，将外围组成员加入进来。同时也要更新智力资本数据库。 add extended team members to the project by updating the project files, database. Also update the Intellectual Capital database. |
| 召集开工会 Kick-off meeting LPDT-83 | LPDT召集 PDT核心组成员和扩展组全体成员举行开发阶段开工会，建议的会议议程如下： 1.项目目标介绍(产品经理) 2.版本开发合同书发布或签字仪式(研发管理办代表/产品线总监/产品经理) 3.PDT任命宣读（产品线总监/项目管理处经理/产品经理） 4.签定承诺书（产品经理和功能部门总监）可选 5.PDT成员相互介绍(全体PDT成员) 6.PDT中角色和职责介绍(产品经理) 7.开发阶段流程以及流程求助渠道介绍(引导者或项目管理处经理） 8.计划阶段回顾和计划阶段交付件介绍（产品经理） 9.开发阶段目标交付件介绍(产品经理) 10.开发阶段工作计划以及重要任务配合和计划风险说明(产品经理) 11.明确开发阶段工作计划、考评和汇报关系、日常沟通方式(产品经理) 12.团队和个人测评指标及激励机制 (产品经理) 13.相关领导动员讲话 LPDT bring together PDTcore team members and extended team members to have a kick-off meeting, with the suggested agenda as follows: 1.brief project objective(LPDT) 2.version development contract issue or signature ceremony (RD management rep/product line director/LPDT) 3.read PDT appointment (product line director/Project Management manager/LPDT) 4.sign commitment letter (LPDT and function department director) optional 5.PDT members introduction to each other (all PDTmembers) 6. introduction of roles and responsibilities of PDT(product manager) 7.brief develop phase process and process help channel(facilitator or Project Management manager) 8.review plan phase and brief plan phase deliverables ( LPDT) 9.brief develop phase objective delivered (LPDT) 10.develop phase work plan , important task coordination & risk description (LPDT) 11.define develop phase work plan, performance measurement ,reporting system and daily communication channel(LPDT) 12.team and individual measurement and incentive mechanism (LPDT) 13. mobilization speech by related leader |
| 执行对外合作计划 Execute external cooperation plan LPDT-91 | 各合作项目经理（产品合作、运营商合作、技术合作）依据对外合作合同/业务计划负责监控实施对外合作计划，保证合作计划与产品开发的同步，并将合作成果应用于产品开发中。 如遇需求变更或计划调整，应按产品开发要求走变更流程，并通过对外合作部/业务部合作分部与合作方达成一致或协调解决。 Each cooperation project manager (product cooperation, carrier cooperation, tech cooperation) responsible for monitoring external cooperation execution, assuring cooperation plan in pace with product development, and use cooperation results to product development according to external cooperation contract/business plan. If requirement is changed or plan adjusted,they should go through change control process,and reach agreement with partners through external cooperation department/functional department cooperation branch. |
| 开始执行项目监控 Begin Monitoring and Control of Project Execution LPDT-90 FPDT-55 RDPDT-65 TSPDT-55 MNFPDT-55 PROPDT-55 MKTPDT-65 SE-125 POP-35 | 协调并跟踪项目任务绩效；跟踪时间进度、成本、资源和交付件；管理项目范围和更改；管理资源，必要的话重新分配资源；必要的话，向上反映问题；定期性地报告项目状态；使用“项目管理”使能流程 Coordinate and track performance of project tasks; track schedules, costs, resources and deliverables; manage scope and changes; manage and reallocate resources if required; escalate issues if required; report status on regular basis; use the 'Project Management' enabling process |
| 监控执行信息安全计划 Monitor and execute Information Security Plan LPDT-95 |  |
| 开始监控产品质量目标和计划Begin Monitoring and Control Product Quality Objective and Plan /PQA-60 | 通过例会、阶段会议、度量分析、交付物审计等，监控质量计划的执行情况。 当实际执行情况与产品质量计划发生偏差时，PQA应提醒LPDT采取相应的补救措施，要求LPDT更新计划。更新后的计划必须经过再次审核和批准。 Begin monitoring and controlling product quality plan by attending PDT regular meeting, end of phase meeting, delivery auditing, metrics analysis etc. When variance is emerged between actual result and initial product quality plan, PQA is responsible to request correcting activities from PDT, PDT should update the product quality plan which should be reviewed and approved once more. |
| 组建Build小组 Setup Build Team RDPDT70 | 开发代表组建Build小组，各开发项目组指定兼职成员加入到Build小组。Build小组负责准备BBIT（Building Block Integrate and Test）的集成方案、用例、环境并负责执行BBIT活动。 RDPDT setup build team, member in IPD-CMM project will join the team part time. Build team is responsible for prepare Building Block Integrate and Test scheme, test cases, environment and perform the BBIT. |
| tracking product target cost 跟踪产品目标成本 FPDT-56 | According to product BOB and procument price,FPDT calculate the product actual cost and the difference from target cost,and then submit the feedback to R&D and procument and IPMT. 根据产品清单和采购价格，FPDT计算产品的实际成本，比较实际成本与目标成本的差距，并反馈给研发、采购和IPMT。 |
| 执行标准计划 Execute standard plan SE-127 | 《产品标准计划》中需要执行的标准工作活动主要有3类：实施标准项目、参加国内外标准会议、标准研究，这些工作在计划和执行过程中都必须配合产品开发阶段的其他活动和国内外标准会议的时间表，并以促进产品开发和增强产品市场竞争力为目标。 There are 3 kinds of standard activities which need to be executed in "product standard plan",that is execute standard project,attend domestic and international standard meetings,standard research, which should coordinate with other activities of product develop phase and domestic/international standard meeting schedule in order to promote product development and enhance product market competitiveness. |
| 优化市场计划 Refine market plan MKTPDT-68 | 根据产品、客户的需求和与产品相关的潜在细分市场，在原有市场计划的基础上进一步分析和细化需要采取的战术性活动， 类似产品在何处销售、需要关注的目标市场、如何更好地贴近和满足客户、如何提升竞争能力等问题都需要详细的描述 （市场策略）以及具体的措施， 包括价格和目标用户。 Based on product and customer requirements and potential market segmentation, further analyze and refine tactical activities which need to be adopted, such as where is the product sold, target market, how to better meet customer's requirements, and how to promote competition ,etc. - all these questions need detailed description (market strategy) and specific measures and steps ,including price and target users. |
| 制定发布计划 Develop Launch plan MKTPDT-69 | 在PDCP通过之后，根据发布策略、具体的发布活动及交付件制定详细的发布计划。 Develop detailed launch plan after PDCP exit based on launch strategy, launch activities and deliverables. |
| 开始EC发布管理，发布初始BOM并纳入EC控制 Begin EC Release Management Release Initial BOM and put it under EC control SE-130 | 将所有技术信息放入数据库并通过正式的工程更改（EC）流程来管理更改；使用“交付件更改管理”使能流程来决定提议的更改，并使用PDM或其它相似的系统来自动管理工程更改（EC release）管理流程。EC release管理并不是冻结数据，而是对更改进行控制，每个人都应该被告知有关的更改以便每个人都基于相同的信息进行工作。 Put all technical information in a database and manage changes through a formal Engineering Change (EC) process; use the 'Deliverable Change Management' enabling process to make decisions about proposed changes and use a PDM or equivalent system to automate the EC release management process. EC release management does not imply the data is frozen, but rather the changes are controlled and everyone is kept informed about the changes so that everyone has the same set of information to work from |
| 对硬件设计进行EC控制 Put Electrical Design under EC Control EE-40 | 所有共享的硬件设计信息，如规格、器件清单、原理图、网表（netlist）、布线图、制造输出等都存放在一个产品数据管理系统之中。任何更改必须通过正式的EC流程，该流程是交付件更改管理使能流程的一部分。在没有准备给其他团队成员共享之前的私人信息存放在特定的项目工作文件下。 All shared electrical design information, such as specifications, parts lists, schematics, netlists, board layouts, manufacturing outputs, etc. are stored in a product data management system. Any changes must go through the formal EC process, which is part of the Deliverable Change Management enabling process. Private information is stored in application-specific, project working files until they are ready for sharing with other team members |
| 对软件设计进行EC控制 Put S/W Design under EC Control SWE-40 | 所有共享的软件设计信息，如规格、原代码、目标代码、测试规格和结果、配置、版本等都存放在软件管理系统中。 任何更改必须通过正式的EC流程，它是交付件更改管理使能流程的一部分。在没有准备给其他团队成员共享之前的私人信息存放在特定的项目工作文件下。 All shared electrical design information, such as specifications, source code, object code, test specs and results, configurations, versions, etc. are stored in a software management system. Any changes must go through the formal EC process, which is part of the Deliverable Change Management enabling process. Private information is stored in application-specific, project working files until they are ready for sharing with other team members |
| 对结构设计进行EC控制 Put Mechanical Design under EC Control ME-40 | 所有的结构设计信息，比如规格、器件清单、布局图、制造输出等都存放在一个产品数据管理系统中。 任何更改必须通过正式的EC流程，它是交付件更改管理使能流程的一部分。在没有准备给其他团队成员共享之前的私人信息存放在特定的项目工作文件下。 All shared mechanical design information, such as specifications, parts lists, layouts, manufacturing outputs, etc. are stored in a product data management system. Any changes must go through the formal EC process, which is part of the Deliverable Change Management enabling process. Private information is stored in application-specific, project working files until they are ready for sharing with other team members |
| 对信息开发文档进行EC控制 Put Documentation under EC Control TD-20 | 所有共享的技术产品文档，比如规格、图纸、有关元器件的技术信息等都存放在一个产品数据管理系统中。任何更改必须通过正式的EC流程，它是交付件更改管理使能流程的一部分。在没有准备给其他团队成员共享之前的私人信息存放在特定的项目工作文件下。 All shared technical product documentation, such as specifications, drawings, technical information about components etc. are stored in a product data management system. Any changes must go through the formal EC process, which is part of the Deliverable Change Management enabling process. Private information is stored in application-specific, project working files until they are ready for sharing with other team members |
| 设计制造工艺 Design Manufacturing Process AME-40 | 评审现有的生产线能力以确定设备和制造工艺的重用程度；评估自动化技术；对工艺进行成本/效益分析；调研开发供制造和测试用的新设备的需求；选择有效的制造工艺和设备并进行制造工艺概要设计。 Review existing manufacturing line capabilities for reuse of equipment and procedures; evaluate automation technologies; perform cost / benefit analyses for technologies; investigate need for developing new equipment for manufacturing and testing; select effective manufacturing technologies and equipment and develop a high level design of the manufacturing process |
| 设计生产测试设备 Design Manufacturing testing equipment AME-45 | 参考装备总体方案和各单板概要设计内容，并考虑到各单板详细设计的规格细化和变更情况，制定各单板的生产测试方案；制定各测试仪的设计规格书。单板生产测试方案主要解决FT中各测试项目如何具体实现以及ICT、老化、软件加载的方法；测试仪规格书主要解决测试仪如何设计出来。以单板生产测试方案和测试仪规格书共同指导后续装备的开发。 Develop the manufacturing testing plan taking into consideration equipment master plan and single board high level design, and specs and changes of single board low level design; develop design specs of all the testing equipment. Single board manufacturing testing plan mainly addresses the execution of FT testing activities and the methods of ICT, aging and software loading; testing equipment specs mainly addreses how the testing equipment is designed. Single board manufacturing testing plan and testing equipment specs will be used together to provide guidance to follow-up equipment development. |
| 供应商选择 Select supplier PRO-20 | 这个活动由CEG根据Sourcing plan 中设定的供应商选择标准和权重进行。CEG将根据项目需要启动供应商选择流程。 This activity is carried out by the CEG using the criteria and weightings set out in the sourcing plan. CEG will initiate the supplier selection process （ISC）if required. |
| 制定市场资料计划 Develop Marketing Information Plan | 在PDCP通过之后，召集营销相关人员讨论要开发的资料，并制定详细的市场资料开发计划。 Convene Marketing members concerned to discuss exploitative materials and develop detailed Marketing information plan afet PDCP exit. |
| 准备发布/局部公开/培训 Prepare for Announcement /Disclosure / Training: MKTE-26 | 开始修改RFA标准模板文档来准备RFA包（市场紧迫性、竞争紧迫性、机会丧失可能性、暴露以前产品的缺陷等）；开始收集信息来完成RFA文档；（RFA意味着向PDT和IPMT施加压力来发布产品，PDT和IPMT在可获得性决策评审点进行检查和平衡）；开始准备对销售员工的培训计划，包括师资培训计划（T3），明确候选客户并准备秘密发布（这些客户可能是早期支持的候选客户）；准备局部发布的材料、信函、保密协议等 Start preparing the RFA (Request For Announcement) package by modifying the standard RFA template document (market demand urgency, competitive urgency, opportunity loss urgency, exposure to previous product defects, etc. ); start collecting information towards completing the RFA document; (the RFA is intended to put pressure on the PDT and IPMT to announce the offering, while the PDT and IPMT provide the check and balance via the Availability DCP). start preparing training programs for sales staff including train-the-trainer programs (T3), identify customer candidates and prepare for confidential disclosures (these customers may be candidates for early support programs); prepare disclosure materials, letters, confidentiality agreements, etc. |
| NetStar启动 Kickoff NetStar MKTE-27 | 召开NetStar开工会，讨论NetStar的开发策略、算法以及初步的开发计划。 Convene NetStar kickoff meeting and discuss NetStar development strategy, algorithm and preliminary plan. |
| NetStar开发计划 Develop NetStar Plan MKTE-29 | 根据开工会讨论的结果，制定详细的NetStar开发计划。 Develop detailed NetStar plan based on the result of kickoff meeting. |
| 确定BETA测试和ESP客户 Identify BETA and ESP customer MKTE-25 | 基于制定的BATA客户选择标准寻找、评估、选择和确定BATA客户。 Looking for, evaluating, selecting and determining BETA customer based on BETA customer selection criteria. |
| 申请产品/模块/单板命名 Apply Parts Naming MKTE-28 | 根据产品命名规则，在命名电子流上申请产品及部件的具体名称。 . |
| 营销类资料开发与评审 Develop and Review Marketing Materials MKTE-29A | 根据营销类资料计划，各责任部门编写资料，并组织相关部门进行评审。 Department concerned compose materials based on Marketing information plan, and organize reviewing meeting. |
| 监控并管理配置及更改 Monitor and Manage Changes SE-140 | 作为持续进行的活动的一部分，对开发和设计活动进行定期性的检查，确保产品需求、规格、配置和其它的产品技术文档没有被随意更改； 使用PDM的EC模块来使产品需求、规格、配置和其它技术文档的更改受控（在PDM实施前，使用CMM和公司其它的相关流程）。 As part of an ongoing activity, perform inspections regularly on design and development activities to make sure that the offering requirements, specifications, configuration(s) and other offering technical documents are not changed in an ad-hoc manner; maintain control over changes to offering requirements, specifications, configuration(s) and other offering technical documents using the structured 'Deliverable Change Management' enabling process |
| 设计检视 Perform Design Inspections: SE-150 | 作为持续进行的活动的一部分，通过参加由硬件、软件、结构、测试、工业设计、采购、市场和其他项目组成员召开的技术会议或阅读会议纪要来进行设计检查；特别的，查实产品是否符合特定的需求和规格，并对所有偏差或更改进行标注；这项活动为“监控和管理配置及更改”活动提供输入。 As part of an ongoing activity, perform design inspections by participating in or reading meeting minutes of regular project technical meetings conducted by electrical, software, mechanical, testing, UCD, industrial design, procurement, marketing, and other project members; specifically look for offering compliance with specified requirements and specifications, and flag any deviations or changes; this activity feeds the 'monitor and mange changes' activity |
| 企业标准、企业内控标准起草 Draft Corporate Standards and Internal Standards SE-156 | 《企业标准》、《企业内控标准》皆源于《产品规格书》，并在开发过程中参照国际、国内标准，运用技术与经济相结合原则，在不增加成本基础上，为达到优于其他制造厂家同类产品质量而选择合适的功能、性能指标编入到标准文本中，两标准的各项指标定位要恰到好处，并要体现层次和梯度：根据国家规定，《企业标准》所列功能、性能指标可优于国际、国内同类标准中相应的部分，而《企业内控标准》在功能、性能指标上必须优于、严于《企业标准》的规定。 Corporate Standards and Internal Standards come form Offering Specs, considering international and domestic standards and based on the principle of align technology with business. Include the proper functional and performance indexes into the documents with a view to reach higher quality than the other manufacturers. The two standards should be positioned properly: according to national rules, Corporate Standards can be higher than similar international and domestic standards, and Internal Standards must be higher and more serious than Corporate Standards |
| 知识产权分析 Intellectual Property analysis SE-158 | 根据项目需要检索专利文献和科技论文，分析其可利用性和专利风险；并确定产品专利申请计划和商标使用方案，以保护公司知识产权。 具体分析内容参见《知识产权分析报告模板》。 Search patent documents and technical papers per project needs and analyze their usability and patent risk; define the patent plan and copywright usage plan to protect Huawei intellectual property rights. Refer to IP analysis template for details. |
| 硬件详细设计 Perform Low Level Electrical Design: EE-60 | 基于硬件概要设计，使用标准的设计工具（根据情形选用RF/模拟/数字/芯片设计）来进行详细设计，描绘出明确的板、卡、元器件、要完成的功能和界面；对每一个板/卡/元器件，开发电路设计，原理图，零部件清单，网表等；按照测试计划合并测试点来支持测试；在数据库中维护设计信息。 Based on the hardware high level design, use standard design tools (RF / Analog / Digital / Chip design, depending on the situation) to perform the low level design that lays out the specific boards, cards, components, functions performed and interfaces; for each board/card/component, develop the circuit design, schematic, part list, net list, etc.; incorporate test points to support testing per the test plan; maintain design information in a database. |
| CAD设计 CAD design EE-65 | 根据详细设计说明书、结构PCB要素图等文档的要求进行PCB板的布局、布线和后仿真。设计完成后投板。具体过程见《PCB设计投板流程》（电子流）。 Perform PCB layout and post simulation based on low level desogn specs and mechanical PCB elements diagram etc. See PCB design and making process (notes) |
| 单元测试 Develop Electricals / Unit Test: EE-90 | 硬件工程师准备好相应的物料，单板PCB投板回来后，逐步加工好单板，进行单板软硬件、逻辑调试，测试单板上模块电路特性是否符合设计要求。 Based on the low level design and the test plans, and depending on RF / Analog / Digital / Chip design, use appropriate design tools to take the circuit design, schematics, parts list, net list, test points, etc., and design board layouts and routings; perform analysis and simulation to identify and resolve problem areas such as hot spots, reliability, etc.; acquire the components, build the boards (either in-house or using a supplier), populate the boards and conduct unit testing; report and fix problems and keep track of changes by updating the documentation in the application-specific project database; report results of build and unit test; identify manufacturability/serviceability/quality/reliability issues and possible fixes |
| 软件详细设计 Perform Low Level S/W Design SWE-50 | 基于分配给软件的需求和规格，使用标准的设计工具（根据情形选用高层次语言，CASE）来进行软件详细设计，描绘出详细的模块、要完成的功能、输入、输出和界面格式。 Based on the requirements allocated to software and the specifications, use standard design tools (high level languages, CASE, depending on the situation) to perform the low level software design that lays out the specific modules, functions performed, inputs, outputs and interface formats; |
| 编码 Develop S/W / Unit Test: SWE-70 | 基于分配的软件需求和规格、软件详细设计，进行编码、链接编辑并且在编程数据库中维护代码及其历史资料。 Based on the low level electrical design and offering specifications, select chip sets for offering subsystems or boards; set up development environments for chip sets; acquire, install and get trained in the use of the programming language/environment for the selected chip sets; based on the allocated embedded software requirements and specifications, develop code, link edit, test and debug code, and maintain the code and its history in the programming database |
| 单元测试 Unit test SWE-72 | 进行测试和调试代码、并且在编程数据库中维护代码及其历史资料。 Test and debug the codes, and maintain the codes and historical data in the program database |
| 结构造型详细设计 Perform Low Level Mechanical Design: ME-50 | 基于分配到结构的需求和规格以及工业设计/人机工程设计的建议，使用标准的设计工具（根据情形选用Pro/E, IDEAS, AutoCAD）来进行详细设计：用结构设计图画出特定的机架子系统、面板、连接件、板、卡、线缆、冷却设备、电源等；在数据库中维护设计信息。 Based on the requirements allocated to mechanical hardware and the specifications, and the briefations from the industrial/ergonomic design activity, use standard design tools (Pro/E, IDEAS, AutoCAD, etc. depending on the situation) to perform the low level design that lays out the specific rack subsystems, panels, connectors, boards, cards, wiring, cooling equipment, power supplies, etc. in mechanical design drawings; maintain design information in a database; |
| 结构试制/试装/测试 Develop Mechanicals / Unit Test ME-70 | 基于详细设计和测试计划，使用合适的设计工具进行强度及振动的细节设计、分析和仿真；获得或构建结构元件，组装成机架（不管是自己还是供应商装），装上各种板并进行单元测试，报告并解决问题，通过刷新特定的项目数据库中的文件来跟踪更改；报告构建和单元测试的结果；明确可制造性/可服务性/质量/可靠性问题及可能的解决办法。 Based on the low level design and the test plans, use appropriate design tools to perform detailed design, analysis and simulation of strength/vibration/; acquire or build the mechanical components, assemble the racks (either in-house or using a supplier), populate with prototype/sample boards and conduct unit testing; report and fix problems and keep track of changes by updating the documentation in the application-specific project database; report results of build and unit test; identify manufacturability/serviceability/quality/reliability issues and possible fixes |
| BBIT(Building Block Integrate and Test) Building Block集成和测试 EE-95, SWE-95, TE-50 | BBIT验证构建模块的外部接口和与其他构建模块之间的接口，包括与已有系统的接口，以及其他需要测试的部分。通过回归测试确保增加新的Building Block后，已有系统能正常运行。 BBIT verify external interface of building block, interface with other building blocks, including the interface with existing system, and other test if needed. Perform regression test to ensure new add in building block is not break the existing system. |
| Hardware Design Analysis 硬件设计审查 TE45 | 对单板硬件原理图、PCB等设计文件作设计审查分析，在底层设计上保证测试对象功能实现上的可靠性与正确性。 测试工程师重点开展的是原理分析和可靠性分析，包括器件可靠性应用分析，系统FMEA分析等。 Analysis design files of Board hardware schematics and PCB. Ensure the reliability and correctness of test objects function realization in low layer design. The accuracy is part TE focus on the analysis of design inspection and performed by EE. TE should focus on logic analysis principle and reliability, including components application reliability analysis, include critical circuit review, critical component usage review, PCB review, EMC and protection review, system FMEA analysis, etc. |
| 测试设计和更新测试计划 Update Test Plan TE-30 | 基于以前制定的测试计划，更新和细化测试计划，包括：硬件、软件和结构测试，测试纲要，测试规格等；指定渐增的构件版本和相应的测试组合；更新的测试计划用于电子、软件和结构的开发与测试 Based on the previously developed test plans, update the test plan details including electrical, software and mechanical tests, test scripts, test specifications, etc.; specify the incremental build versions and their respective test suites; the updated test plans are used in the development and testing of the electrical, software and mechanical product |
| 开发“开发用”测试工具 Develop "Development" Test Equipment TE-40 | 基于测试计划，设计和开发“开发阶段”使用的测试装备；识别标准/非标准测试装备、测试设备和测试程序；获得和保护测试装备和工具来支持开发测试。 Based on the test plans, design and develop test equipment for use during development; identify standard/non-standard test equipment, test fixtures and test procedures; acquire or secure testing equipment and facilities to support development testing |
| 单版测试 Single board test TE-45 | 硬件开发工程师完成硬件单元测试后，测试人员对单板进行全面的测试，包括单板硬件测试、单板软件测试、逻辑测试，保证单板硬件功能实现上的正确性与可靠性。 After HW engineer completed HW unit test, the test engineers conduct overall testing, including single board HW test, single board SW test, logical test to ensure the accuaravu and stability of single board function execution. |
| 信息开发 Develop Information TD-30 | 基于详细设计和开发活动编写技术文档、操作手册、使用手册参考文档、在线支持文件/资料等。 Develop technical documentation, operation manuals, usage manuals reference documentation, online support files/data, etc. based on the low level design and development activities |
| 翻译 Perform Translation TD-40 | 基于行销的NLS需求（地理、语言）将技术资料翻译成合适的语言；需要时利用第三方（第三方需要签定保密协议）。 Based on the marketing NLS requirements (geographies, languages) translate the technical information into the appropriate languages; use third parties as required (third parties have to sign a non-disclosure agreement) |
| 信息产品测试 information product test TD-42 | 利用内部环境对信息产品的实用性、可用性、一致性进行测试 to the appendix "activity description". And the activity description is: Making use of internal environment, test the practicability, usability and consistency of the information prodcut. |
| 下达原型机物料计划 Notify prototype parts plan AME-46 | 在计划阶段技术评审3后，根据产品物料需求计划，启动原型机物料申购工作，此活动一直持续到产品开发阶段技术评审4。按照相应的物料下达方式，由硬件工程师完成器件（包括委托设计电源）申购、PCB投板，配套设备、软件申购工作，结构经理完成结构样件试制申请等工作。 Following TR3 in plan phase, initiate procurement of prototype commodity according to the offering commodity requirements plan, which will be lasting till TR4 in develop phase. Per the different order placements, HW engineers perform parts purchase including outsourced power supply, PCB making, accessories,SW purchase, mechanical piloting,etc. |
| 产品数据准确性管理与齐套 Accuracy mgt and completeness of product data SE-157 | 根据产品配置和一级计划，确定产品数据交付件；根据产品详细设计，调整优化产品数据结构；EC的一致性管理与发布，包括跨产品线产品数据的关联应用；监控产品数据交付件按计划归档，产品数据齐套性检查；PART信息、BOM清单、技术文件、中试文档的准确性管理与齐套发布；及时处理产品数据问题；推广产品数据的新技术、新工具的应用，培训相关产品数据知识。 Based on product configuration and L1 plan, define product data deliverables; based on offering LL design, modify and refine product data structure; mgt and release of EC consistency, including the use of cross-product-line product data; monitor the timely documentation of product data deliverables and inspection on product data completeness; accuracy mgt and complete release of part information, BOM, technical documents and D&P documents; timely address product data issues; deploy new product data technology and tools, and perform related training. |
| 技术评审4 Perform Technical Review 4 SE-160 PQA-70 | TR4保证Building Block用于系统级构建之前是完整的。对于一次构建（Build）涉及到的每一个Building Block，应该有且仅有一次TR4对其进行评审。任何不符合规定的情况都应该在TR4问题记录中得到记录，并进行风险评估。 TR4 focuses on ensuring Building Block integrity prior to the use of a building block as part of system level build verification (SDV). Every Building Block must be reviewed as part one and only one TR4 event prior to its use in conducting SDV for a particular build. Any deviation from this should be reflected in the TR issues log, and a suitable evaluation of risk in proceeding evaluated. 一个IPD项目可能有1个或多个TR4。根据《产品Build划分方案》（该文档应该在计划阶段退出前完成），可以裁减项目计划中的相应活动（包括TR4评审点），并对《TR4 Checklist》中的评审要素也进行相应的裁减。There can be one or more TR4s associated with an IPD project. The project plan must be tailored to identify building block verification and TR4 events in conjunction with The System Build plan, and TR4 checklists suitably configured to reflect this plan prior to Building Blocks' Plan of the product should be completed before plan phase exit. TR4：在Building Block完成BBFV后，对该Building Block是否满足SDV的进入标准进行评估。TR4 is carried out after BBFV has been completed to evaluate whether the Building Block can meet the SDV entry criteria. TR4要检查Building Block所包含模块（Module）的详细设计审查结果、单元测试（UT）结果、模块集成测试（MIT）结果、模块系统测试（MST）结果、以及该Building Block的BBFV验证结果。TR4 will use the TR4 Checklist to confirm LLD review results, UT results, MIT results, MST results of all modules included in the Building Block, and the Building Block's BBFV results. TR4包括如下的活动： TR4 encompasses the following set of activities: a. TR4计划制订、TR4准备，包括《TR4 Checklist》、评审会议议程、与会人员确定及准备、会议讲解胶片、会前资料分发、sub-TR问题记录、TR4评审报告以及其他相关材料；Planning & Preparation of the TR4 event, including checklists, review session agenda, attendee designation and preparation, presentations, handouts, sub-TR issues log, the TR4 Review Report, and other materials b. 召开TR4评审会议，以及相应的沟通； Conducting the TR4 meeting and associated communications c. 草拟TR4风险评估结果、改进计划、后续活动建议；Preparation of TR4 assessment, action plan, and recommendations d. TR4相关交付件的管理；TR4 related issues management e. 如果TR4评审会发现有更改的情况，要准备PCR或其他类型的更改请求；Preparation of PCRs or any other change documentation resulting from sessions. f. TR4评审报告的草拟及授权签发。 TR4 Review Report preparation, authorization and release. TR4的目的在于The objective of TR4 is to: a. 判断该Building Block能否进入SDV；Determine whether a particular Building Block or set of building blocks is suitable for SDV. b. 确保SRS分解到该Building Block所包含的所有模块（Module）的相关规格已经在模块（Module）详细设计中体现； Ensure that the specifications of all modules included in the Building Block, which were decomposed from SRS, had been realized in the modules' LLD, c. 检查sub-TR是否已经对各Building Block内部以及各Building Block之间的问题进行了检查，并将结果记录到sub-TR评审报告中； Check that intra and inter discipline building block elements have been fully integrated and reviewed prior to BBFV, as represented by documented sub-process Technical Reviews. d. 记录《TR4 Checklist》中不符合的评审要素，确定对下一步开发活动的影响，给出是否继续进行相应活动的建议。Record any issues of non-compliance to TR4 Checklist items. and to determine and make recommendations regarding the impact of going forward with development. |
| 更新BOM 并在初始生产前向制造发布（SIT和BETA系统) Update BOM and release to manufacturing before initial production (SIT systems and beta) SE-161 | PDM活动. 在IPD流程的各个关键点，产品构造的最新情况应提供给制造。另外在Windchill PDM系统这边，基线就用来创建产品状态的“快照”，这样共享产品数据的用户可以共享同一既定的产品配置。 PDM activity. The latest level of a product's contents should be made available to manufacturing at every key point in the IPD Process. Additionally,within Windchill, the PDM system, a "baseline" is used to create a "snapshot" of a product's status so that users sharing product data can do so within the context of a known product configuration. |
| 技术支援准备 Prepare Tech Support TSS-30 | 准备培训资料，就新产品对技术支援的同事进行培训；参与测试（包括beta测试），学习产品和如何对安装、配置和开通、操作、故障检测、诊断、解决和管理等进行技术支援（参见前述的技术支援计划）。 Prepare training materials, train tech support staff on new offering; participate in testing including beta testing and learn about the offering and how to provide tech support for installation, configuration and set up, operation, problem detection, diagnosis, resolution and management, etc. (see previous tech support plan) |
| 准备可安装性/可服务性测试 Prepare installability/serviceability test TSS-38 | 确定可安装性/可服务性测试的测试项目，搭建测试环境，准备测试资源等。 Define installability/serviceability test items, set up test environment and prepare test resources,etc. |
| 订购原型机物料 Order Prototype Parts PRO-30 | 在和主要供应商谈判之后，订购原型机物料（假定技术资料——图纸、规格等在EC控制之下）；这是风险释放，当产品包开发通过EC流程逐步进行更改时，供应商将及时得到更新信息。 After negotiating with key suppliers, order prototype parts (assuming that the technical information - drawings, specifications, etc. are under EC release control); this is a risk-release, and the supplier is kept updated on incremental changes as the offering development proceeds via the EC process . |
| 企业标准、企业内控标准定稿 Finalize Corporate Standards and Internal Standards SE-162 | 优化《企业标准》、《企业内控标准》初稿，进行定稿。 Refine Corporate Standards and Internal Standards drafts and finalize the versions. |
| SDV（系统设计验证） System Design Verification EE-120 SWE-110 ME-110 TE-55 | 按更新的测试计划，整合渐增的产品构件版本并按计划进行测试；验证产品是否符合原先规定的功能。 Per the updated testing plan, assemble incremental build versions of the product and conduct testing per the plan; verify that the product performs the functions as specified. |
| 可安装性/可服务性测试 Installability/serviceability testing TSS-40 | 按已定的测试项目进行测试。 Conduct the testing per the planned testing items. |
| 下达初始产品物料计划 Notify initial product parts plan AME-47 | 在技术评审4后，根据调整后的产品物料需求计划表中确定的初始产品需求规模、时间、产品配置关系，物流计划员负责从单板BOM清单中提取专用物料、公用物料，按规范制定物料计划。计划文件经相关人员审核、会签、批准后下达。 After TR4, based on initial products requirement, time, product configuration defined in the update offering commodity requirement plan, logistics planner gets special and common parts from single board BOM, and develop parts plan. Distribute the plan after being reviewed, signed and approved. |
| 订购初始产品物料 Order initial units parts PRO-39 | 在和主要供应商谈判之后，订购初始产品物料（假定技术资料——图纸、规格等在EC控制之下）；这是风险释放，当产品包开发通过EC流程逐步进行更改时，供应商将及时得到更新信息。 After negotiating with key suppliers, order initial units parts (assuming that the technical information - drawings, specifications, etc. are under EC release control); this is a risk-release, and the supplier is kept updated on incremental changes as the offering development proceeds via the EC process . |
| 试制准备 Prepare pilot prodcution PP-05 | 在试产准备过程中通过熟悉产品完成产品整机、单板、模块的3种指导书的拟制；制订产品制造系统验证方案和产品一致性验证方案。对产品在制造系统方面和产品一致性方面进行评估，并关注用生产线试生产（该生产线就是用来生产新产品的生产线，以便评估生产线）， 完成试产规划报告为生产初始产品作好准备， 并保证顺利通过技术评审4A。 Develop three instructions for system, single board and module; develop mfg system verification plan and units consistency verification plan. Focus the pilot production in the production line which is used to produce new products to assess the line. Develop pilot production plan report to be ready for initial units production, and ensure the success of TR4A. |
| 开发生产测试设备 Develop "Manufacturing" Test Equipment AME-50 | 基于更新的测试计划，提供质量、可靠性、环境和其他性能、鉴定等方面的需求，承诺的销售量，设计和开发在生产过程中使用的测试装备；确定标准/非标准测试装备，测试夹具和测试程序；在生产过程中，获得测试装备和工具来支持测试。 Based on the updated test plans, offering requirements for quality, reliability, environmental and other performance, certification, etc., and committed sales volumes, design and develop test equipment for use during manufacturing; identify standard/non-standard test equipment, test fixtures and test procedures; acquire or secure testing equipment and facilities to support testing during manufacturing |
| 开发制造工艺 Develop Manufacturing Process AME-60 | 基于所承诺的销售量设计制造工艺流程；与采购人员一起进行“自制/购买”分析，决定外购供应商；评估现有的制造设备和工具的符合度、容量、能力、可获得性等，根据需要选择额外的生产设备，布置生产线，设计工艺路线，模拟并反复平衡生产线；获得、安装、集成并测试生产线；准备生产初始产品。 Based on committed sales volumes develop the manufacturing process; work with procurement and perform make/buy analysis; make decisions regarding outsourcing to suppliers; evaluate existing manufacturing equipment and facilities for fit, capacity, capability, availability, etc., and select additional manufacturing equipment as necessary; layout the manufacturing line, develop routings, simulate and rebalance manufacturing lines; acquire, install, integrate and test manufacturing lines; prepare lines to produce initial units |
| 技术评审4A Technical Review 4A SE-165 PQA-80 | 在SDV完成后，对产品技术上的成熟度进行评估，确保所有存在的问题和风险都进行了评估，并生成了相应的改进计划，以保证供应和制造能力足以支撑初始产品生产活动。TR4A is carried out after SDV has been completed to evaluate product maturity and ensure that any problems & risks have been determined and an action plan developed, and to ensure that supply and production capability has been assessed and is sufficient, prior to the initiation of pilot production. TR4A作为IPD流程中一个关键的技术评审点，其目的包括： As a key review point in the IPD process flow, the purpose of TR4A is to: a. 对SDV测试结果、遗留问题及风险、改进计划进行评审，判定是否进入SIT；Review SDV test results, issues and risks, action plan, for deciding on whether to enter SIT; b.评估原型机的成熟度是否可以进入初始产品测试；Assess whether the prototype is mature enough to justify initiating pilot production and testing. c.根据进行TR4A评审的产品版本所具有的有限的功能和性能规格，判断该版本是否适合启动Beta测试；Determine whether the product, or a version of the product with limited functional and/or performance attributes, is suitable for producing and testing a Beta unit. d.对采购和制造能力进行基线化，保证足以支撑初始产品生产（从而保证SIT的启动），以及开发阶段的Beta测试活动（如果需要进行Beta测试）。Baseline procurement and production capabilities, and ensure that they are sufficient to support pilot production of units for SIT and Development Phase Beta test events, as required. TR4A针对一个Build版本进行，TR4A应该在该Build启动初始产品生产和启动Beta测试之前进行。 It is required that TR4A be conducted for a given build configuration prior to the producing and submitting a unit based on that build for Beta test. |
| 更新BOM并发布最新版本给制造 (SVT和beta)系统用 Update BOM and release latest version to MFG (for production of systems for SVT and beta) SE-170 | PDM活动. 更新BOM并发布最新的版本到制造（生产SVT和Beta测试用的系统） 描述：在IPD流程的各个关键点，产品构造的最新情况应提供给制造。另外在Windchill PDM系统这边，基线就用来创建产品状态的“快照”，这样共享产品数据的用户可以共享同一既定的产品配置。 PDM activity. Description: The latest level of a product's contents should be made available to manufacturing at every key point in the IPD Process. Additionally, within Windchill, the PDM system, a "baseline" is used to create a "snapshot" of a product's status so that users sharing product data can do so within the context of a known product configuration. |
| 下达RAMP UP 产品物料计划 Notify ramp up units parts plan AME-61 | 在技术评审4A后，根据ESP专员提供的经评审的ESP计划，物料计划工程师制定RAMP UP产品物料计划文件，按照相关计划操作流程进行排产、下达专用物料采购计划（包括PCB、结构件、外购设备、软件）、制定专用物料半成品加工计划。以后每两周根据调整的ESP计划与开发设计更改信息滚动刷新RAMP UP产品物料计划。到发布阶段RAMP UP产品启动生产前，及时检查RAMP UP产品的物料齐套性。 After TR4A, based on the reviewed ESP plan, parts planner develop ramp up units parts plan and schedule production per operation process and notify special; parts order plan including PCB, mechanical parts, OEM and SW, and develop semi-finished special parts processing plan. Later on, update the plan bi-weekly per update ESP plan and design change information. Before initiation of ramp up units in launch, check timely the completeness of ramp up parts. |
| 订购RAMPUP产品物料 Order ramp up parts PRO-45 | 在和主要供应商谈判之后，订购RAMP UP产品物料（假定技术资料——图纸、规格等在EC控制之下）；这是风险释放，当产品包开发通过EC流程逐步进行更改时，供应商将及时得到更新信息。 After negotiating with key suppliers, order ramp up parts (assuming that the technical information - drawings, specifications, etc. are under EC release control); this is a risk-release, and the supplier is kept updated on incremental changes as the offering development proceeds via the EC process . |
| 生产初始产品 Produce initial units PP-10 | 利用开发完成的产品制造工艺，生产小批用于测试的产品单元；借此机会来微调工艺流程。 Using the manufacturing process developed for the offering, produce small number of units for testing purposes; use the opportunity to fine-tune the process |
| 制造系统验证 Mfg system validation PP-15 | 利用开发完成的产品制造工艺，生产小批用于测试的产品单元；借此机会来微调工艺流程，并通过对制造系统的验证工作进行有效的指导和控制，以保证验证效果，提高验证效率，按时完成验证计划。 Leverage the developed mfg process to produce a few units for testing in order to finetune the mfg process, and guide and control the mfg system to complete the validation plan timely. 组织实施产品在试产验证过程中制造系统验证数据的分析处理和产品一致性测试，完成对产品在制造工艺系统方面和产品一致性方面的评估，以及各种问题的及时分析总结、反馈和处理，并跟踪至彻底解决。 Perform data analysis and units consistency testing when conducting pilot validation to complete mfg process assessment and consistency assessment, and timely analysis, feedback and processing of all the issues,tracking till ultimate solution. |
| SIT（系统集成测试） System Integration Test EE-140 SWE-130 ME-122 TE-60 | 基于测试计划（渐增的构件和测试），逐步构建系统并对从生产线生产出来的首批产品单元进行集成测试（渐增测试和最后的全面测试）。验证产品是否符合原先规定的功能。 Based on the test plan (incremental build & test), build systems incrementally and perform integration testing (incremental testing and final overall testing) on the initial units produced on the manufacturing line. Validate whether the product meets the originally defined functions. |
| 可安装性/可服务性测试 Installability/serviceability testing TSS-41 | 按已定的测试项目进行测试。 Perform the testing per the developed testing items. |
| BETA测试准备 Prepare BETA testing TSS-42 | 进行安装工具准备、人员培训、勘测、工程计划、发货跟踪等BATA测试的各项准备工作。 Prepare installation tools, training, site inspection, installation plan, shipment tracking, etc. For Beta test. |
| 技术评审5 Perform Technical Review 5 SE-230 PQA-90 | TR5是在发布给客户前对项目整体状态在设计稳定性和技术成熟度方面的独立评估活动。TR5目的是确保产品符合预定的功能和性能要求，以满足前期确定的产品包需求。 TR5 serves as an Independent assessment of overall project status with focus on evaluating design stability and readiness to begin customer ship level builds (Qualify Phase). The purpose of TR5 is to ensure that the product fully meets specified functional and performance criteria, and meets product offering requirements identified prior to development. TR5在SIT结束后进行，TR5要保证产品在试制前在功能和性能方面的问题均已发现和解决： TR5 is done right after SIT. It ensures that all issues in meeting product functional and performance criteria have been addressed and solutions properly integrated into the the 1st article manufactured by the Pilot Production line: a. 检查初始产品的规格是否符合计划阶段产品规格的要求； the initial production units are evaluated to ensure that they meet the system specifications defined in the Plan phase. b. 检查初始产品的制造过程是否影响产品的功能、可靠性和性能规格。 The initial production units are checked against the prototype units to make sure that the production process does not impact functionality, reliability, or performance. TR5是进入验证阶段的必要和充分条件。完成TR5就表明小批量初始产品生产和销售已经准备就绪。 TR5 is necessary and sufficient criteria for entry into qualify phase. Completion of TR5 indicates everything is in place to initiate production of small quantities of products for sale. |
| 根据UCD原型评估系统详细设计 Evaluate System Detailed Design Against UCD Prototype UCD－80 | UCD团队成员分别与将来实现该部件的人员一起在用户整体体验（TUE）概念设计的基础上进行细化 the UCD Team fleshes out the conceptual design and works with those who will implement the designs. 组织公司内部的领域专家,从规范、标准、原则、设计指南方面评估已经完成的TUE(用户整体体验)详细设计。 Inspect a detailed design with regard to design specifications,standards, principles, and guidelines.This is Performed by an expert,Usually performed prior to user testing. Focus is on consistency with known principles and guidelines for design. 使用高保真度的产品模型，通过用户评估，进而改进已经完成的TUE(用户整体体验)详细设计. Using High-fidelity prototypes enable the testing of the details of the design until all major design issues are resolved.. |
| UCD设计验证 UCD Design Validation UCD－90 | 通常使用高保真度的原型或Alpha版本，通过用户对整个TUE(用户整体体验)详细设计进行测试，获得主观和客观的度量数据，明确是否达到概念阶段确定的可用性目标以及是与竞争对手进行对比. A Design Validation is a test of the detailed design of the offering. Performed under controlled conditions,Often uses high-fidelity prototypes or alpha-level versions of the offering Objective and subjective measures are taken. Compared to competitor benchmarks |